## Slide 1: Stakeholder Power Analysis
Participatory Mapping
By: Samuel Musembi Musyoki
Unit: M04U03
Notes: <number>

## Slide 2: Outline of the presentation
Introduction
Stakeholder power analysis and its uses
Doing stakeholder power analysis: a stepwise approach
Notes: <number>

## Slide 3: Introduction
Communities have many diverse stakeholders with interests and abilities to influence the process and decisions.
The nature and level of their engagement depends on whether they perceive the process as threatening or supportive.
Notes: <number>

## Slide 4: Stakeholder power analysis and its uses
Stakeholders are individuals, groups, organisations or agencies that will affect, or will be affected by, the participatory mapping project and its outcomes.
Notes: <number>

## Slide 5: Stakeholder power analysis and its uses
Some examples ...
Some considerations ...
Notes: <number>
Some examples:
People who live in or near the relevant forests, people who live further away but who use these forests, forest officials, timber company managers, environmentalists, politicians, public servants, national citizens, consumers, forest authorities, central government agencies, local government agencies, national NGOs, academics, researchers and donors
Some considerations:
Their interests in forests are legitimate.
One role of a stakeholder power analysis might be to examine the legitimacy of their claims.

## Slide 6: The stakeholder power analysis
A tool used to give an overview of all players connected to an intervention.
It identifies, analyses and takes into account their interests and expectations related to the intervention.
Notes: <number>
Players connected with an issue, a project or intervention (e.g. participatory mapping) in one way or another
Interests and expectations of people, groups or organisations significant to the issue, project or intervention (e.g. participatory mapping)

## Slide 7: Doing stakeholder power analysis
A stepwise approach:
  Develop purpose and procedures of analysis and initial understanding of the system
  Identify key stakeholders
  Analyse stakeholders’ interests, characteristics and circumstances
Notes: <number>
See M04U03 Handout 4T for a detailed description of these steps.

## Slide 8: Doing stakeholder power analysis
A stepwise approach:
  Identify patterns and contexts of interaction between stakeholders
  Assess stakeholder power and potential
  Assess options and use the findings to make progress
Notes: <number>

## Slide 9: Doing stakeholder power analysis
Who are potential constituencies of this participatory mapping initiative?
Who might be adversely affected by the process and its outcomes?
Who has existing rights (e.g. sacred places, water springs, grazing land, etc.)?
Who is likely to be voiceless during and after the process?
Notes: <number>
For further information and tips for responses to these questions, refer to the handout and exercise on stakeholder and power analysis.

## Slide 10: Doing stakeholder power analysis
Who is likely to resent this mapping process and mobilise resistance against it and against what needs to be done?
Who is responsible for the plans intended to come out of this participatory mapping process?
Who has resources, skills or key information needed for this mapping initiative?
Notes: <number>

## Slide 11: Doing stakeholder power analysis
Whose behavior has to change for the success of the participatory mapping initiative?
What will need to be done to ensure support and participation by all?
Notes: <number>