## Slide 1: Assembling a Core/Implementation Team
The size and composition of a Core Team
By: Mac Chapin and Natalia Martens
Unit: M07U01
Notes: Please refer to the M07U01 Handout for Trainee and to recommended readings for more information on this topic.

## Slide 2: Introduction
Size and composition of the Core Team depend on the magnitude and complexity of the project
A Core Team must be inclusive and efficient
Notes: The Core Team must be inclusive, representing the communities and leadership of the project area and the technology intermediaries. It must also be efficient, so that decisions can be made in a clear and timely manner. Usually projects with strong administration succeed, while those with loose, weak administration run into problems.

## Slide 3: Members of the Core Team
Team leader/coordinator
Administrator
Lead cartographer/GIS specialist
Subject matter specialist(s)
Community leaders
Notes: Usually a Core Team includes these members.
Subject matter specialists may include professionals in natural resource management, biodiversity, agriculture, forestry, anthropology, sociology, linguistics, community development, communication or other fields.

## Slide 4: Team leader/coordinator
Community leader or qualified and respected outsider
Contracted for the entire project cycle
Responsible for:
  the functioning of the project
  coordination of the participating parties
Notes: The team leader (TL) should be either a community leader or a qualified and respected outsider.
The TL has to be contracted from early ground preparation through to the production of the maps and possibly through post-mapping activities.

## Slide 5: Administrator
In charge of:
  project finances
  logistical arrangements
  bureaucratic details of the project

## Slide 6: Lead cartographer/GIS specialist
Person in charge of the technical unit
Responsible for:
  gathering all the cartographic materials
  setting up the laboratory (if needed)
  selecting technical staff
  supervising the technical work
Notes: If the cartographer does not belong to the cultural group being mapped, s/he should have the following characteristics:
  - sound technical skills;
  - specialised interest in working with indigenous or traditional people;
  - excellent interpersonal skills and a facility for working with people from different cultures;
  - knowledge of the region being mapped.

## Slide 7: Community leaders
Represent and protect the interests of the people whose resources are mapped
Handle communication: serve as “bridge” between the communities and outsiders
Coordinate participants at the community level

## Slide 8: Community leaders
Coordinate villagers responsible for gathering, geocoding and mapping information
Must be recognised community leaders
Should not be selected by outsiders

## Slide 9: Conclusion
The Core Team should
  not be imposed
  ensure smooth and effective management of the project dealing with different stakeholders
  have a composition and structure that conform with local customs and values
Notes: Stakeholders could include the participating communities, the technology intermediaries, government agencies, non-governmental organisations, etc.