## Slide 1: Project Design and Financing
By: Mac Chapin and Natalia Martens
Unit: M07U02
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>
Please refer to the M07U02 Handout for Trainee and to recommended readings for more information on this topic.

## Slide 2: Introduction
Participatory mapping projects:
  are technical and social-organisational exercises that involve a number of actors;
  involve several components to be performed in different places;
  require careful planning;
  should be presented in a project format that meets the expectations of the funding agency and includes a budget.
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>
Actors include non-governmental organisations and government agencies.
Project components within the communities include information gathering, sketch map making and 3-D modelling). Components far from the communities (e.g. in towns or cities) include GIS, cartography and printing of maps.

## Slide 3: Designing the project
Essential elements of a project proposal:
  the project rationale
  implementation methodology and schedule
  units costs and quantities and budget
The project proposal is used to seek financial support.
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>
The project rationale includes the purpose/objective, expected results and related activities.

## Slide 4: Project purpose
The project purpose represents the solution for the problem’s root causes which the initiators have identified.
Maps can serve multiple purposes, but there is generally a primary reason for mapping one’s lands.
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>
Participatory mapping projects are carried out with one or more purposes in mind. These should be clearly defined in the minds of everyone involved.
Refer to the previously completed exercise “Project Rationale via Problem Tree Analysis”.

## Slide 5: Project design and proposal
Project design: deals with all issues (including sensitive issues) as perceived by the project initiators
Project proposal: is tailored for outsiders (e.g. funding agency) and so handles purposes in a more palatable fashion
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>
Project design is one thing; the project proposal is something else. Project design will contain an open discussion of the purposes, no matter how political these may be; the project proposal will be much more circumspect and handle the purposes in a much more palatable fashion.

## Slide 6: Outcomes
Products (maps)
Processes
  bringing people together
  generating community cohesion
  learning by doing and exchanging
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>
Maps are the products of any mapping project. Participatory mapping projects are also processes that bring people together in a creative, purposeful manner. The outcomes of participatory mapping projects are products and processes; it is often said that while the produced maps are useful, the real benefit is the process that comes into being during the quest for the maps.

## Slide 7: Methodology, mapping methods and actors
Scope of the mapping initiative
Mapping methods (e.g. 3-D model, sketch map, use of remote-sense images, GIS)
Who will be involved?
Where will it take place?
What is the time frame?
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>
The methodological approach and the choice of the mapping method vary depending on the area covered, the technical capabilities of the actors involved and the resources available. This should be the most detailed section of the project design. It is the technical component of the project. More details about the choice of mapping method(s) are provided in Module M06.

## Slide 8: Budget items
Local salaries, fees and honoraria
Travel expenses
Workshops (venue, food and accommodation)
Cartography (materials, supplies and equipment)
Documentation (supplies, equipment, processing, editing, translating and publishing)
Services (map design and printing)
Follow-on work
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>
Here are some examples of budget items:
  local salaries/fees/honoraria (e.g. for community researchers, Core Team members, cartographers/GIS specialists);
  travel (e.g. travel related to pre-project logistics for villagers, community leaders, cartographers, etc.);
  workshops (e.g. food and lodging requirements for participants, facilities for workshops);
  cartographic materials, supplies, equipment (e.g. base maps, aerial photographs, satellite images, paper, pens, coloured pencils, drafting tables, lamps, etc.)
  equipment and materials for documenting the mapping process (e.g. video/audio recorder) and services (e.g. data processing, report writing, video editing, publishing, etc.);
  map design and printing (e.g. durable maps for communities, maps for wider distribution);
  follow-on work (e.g. networking, communication, advocacy).

## Slide 9: Prerequisites for success
Clear project design
Well-designed budget
  covering full project implementation
  including contingencies to address changing circumstances
Availability of funds to cover project implementation before project begins
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>

## Slide 10: Conclusion
A clear, well-articulated project design is similar to a good road map: if followed, it will get project initiators where they want to go
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>