## Slide 1: Arranging Project Logistics
By: Mac Chapin
Unit: M07U05
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>
Please refer to the M07U05 Handout for Trainee and to recommended readings for more information on this topic.

## Slide 2: Introduction
Project logistics cover:
  workshop venues (which are often in cities);
  travel by community members and technical staff;
  signing contracts for workshop space and accommodations for participants;
  procurement of equipment and materials;
  production and distribution of outputs.
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>
A variety of logistical arrangements must be made so that the project can run smoothly. These arrangements must be made in a timely fashion; many must be in place before project activities get underway.

## Slide 3: Sketching out logistical requirements
The logistical requirements are based on the project proposal and budget.
Close attention should be paid to:
  the trajectory of the project;
  the funds allotted for the various budget items.
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>

## Slide 4: Travel
Most communities are often located in remote areas with difficult access.
Travel can be by bus, boat, airplane or a combination of these methods, and at times it can become very complex.
Travel must be addressed early in the project to make sure that transportation will be available.
International travel also needs to be firmed up before project activities begin.
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>

## Slide 5: Workshops
An appropriate space for the workshop needs to be found.
Participants from distant locations must be provided with board and lodging.
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>
Appropriate workshop space may be a school or a community meeting hall.

## Slide 6: Research materials, supplies, equipment and services
There is a constant need for:
  cartographic materials (e.g. aerial photographs, satellite images, base maps, etc.);
  paper, pencils, pens, white out, erasers, paint, cardboard, glue, tape, printer cartridges and a variety of other supplies.
Equipment needs to be rented or bought.
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>

## Slide 7: Printing the final maps
The final maps need to be professionally designed and printed.
In some countries and regions, no adequate facilities exist and it is necessary to find a printing firm abroad.
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>
It is often not an easy task to locate adequate printing facilities.

## Slide 8: Conclusion
Two broad types of logistical arrangements:
  those that require considerable lead time and must be made in advance
  the many small actions that must be made on an impromptu daily basis
Notes: Support the spread of “good practice” in generating, managing, analysing and communicating spatial information
<number>