- Unit M15U01 - Evaluating and Reflecting on the Process

Unit Trainer Notes

Outlined by: Luigi Assom, Mac Chapin, Barbara Codispoti, Renato Emerson, Peter Kuria Githinji, Adrian Lasimbang, Julius Muchemi Denise Senmartin (facilitator), Aurelio Vianna, Giacomo Rambaldi and Giulia Pedone

Developed by: Nigel Crawhall

| Introduction | This Unit focuses on the monitoring, evaluation, reflection and learning processes that should accompany participatory spatial information and communication processes. The Unit introduces the trainee to key concepts and tools relevant to planning, monitoring and evaluating the participatory mapping cycle and its application in advocacy or change processes. The focus is on tools which help the implementation team understand, reflect on and manage the social dynamics and project planning required for effective use of the maps. It is important to focus not on the success of the actual mapping, but on the end goals: Did the mapping help the community achieve its aims? Did the mapping have an overall beneficial effect? Was any harm done by this project? What were the lessons learned? Did the mapping increase the ability of the community to advocate for its rights and protect the integrity of the local ecosystem on which it relies or for which it feels responsible? This Unit is useful for those developing grant proposals for participatory mapping, monitoring project implementation and evaluating results. |
| --- | --- |
| Target audience | Technology intermediaries working in multidisciplinary teams and operating within an institution/organisation already committed to practising participatory mapping and who are or would be required to: (i) deliver training on the practice, (ii) facilitate the process in the field. |
| Unit objectives / expected outcomes | After the completion of the Unit the trainee will be able to: - discuss the importance and implications of good planning and appropriate planning methodologies; - describe the monitoring and evaluation cycle; - apply monitoring tools, including objectively verifiable indicators and risk analysis; - conduct project evaluations; - implement democracy walls. |
| Keywords / key concepts | Monitoring, evaluation, indicators, progress, milestones, recommendation, action plan |
| Content outline, main topics covered and suggested sequencing | This Unit focuses on the topics listed below: - Evaluating and reflecting on the map-making process (Handout4T & PPT No. 1) (45 min) - Results, indicators and objectively verifiable indicators (Exercise No. 1) (75 min) |
| Components of the Unit | - Exercises - Exercise No. 1: Results, indicators and objectively verifiable indicators; to sort through project plans, clarify indicators for results and develop appropriate objectively verifiable indicator (OVI) tools (75 min) - Handouts for Trainee: (to be distributed in printed format) - Evaluating and reflecting on the map-making process (Handout4T) - Article: Democracy walls - List of Additional Resources - Glossary - Multimedia - None - Presentations (PPT) - PPT No. 1: Evaluating and Reflecting on the Map-making Process; How to apply an appropriate Planning, Monitoring and Evaluation methodology to advocacy and related processes. (45 min) - Unit Glossary - Included |
| Duration | 2 hours |
| Prerequisite skills / knowledge | Prior knowledge of Logical Framework Approach or similar methodologies is an advantage |
| Pre-Unit activities | None |
| Additional trainer resources | Jules N. Pretty, Irene Guijt, Ian Scoones and John Thompson. 1995. Participatory Learning and Action: A Trainer’s Guide, IIED, Participatory methodology series, IIED, UK. |
| Equipment needed | Computer and data projector, Internet access, flip chart and writing implements, meta-cards, felt-tip pens |
| Comments | Consider the advice provided in Module M03. See relationship to Module M07. |